PROJECT PLAN — v2.0

Ready or Left Behind?
AI in the Charity & Nonprofit Sector: Adoption, Gaps, Bias & Governance

| Project Owner | Elvira | Version | 2.0 — April 2026 |
| --- | --- | --- | --- |
| Start | Friday 11 April 2026 | Target End | Friday 29 May 2026 |
| Tool | Power BI (work licence, personal use) | Publish | Power BI Public + GitHub + LinkedIn |
| Total sessions | 8 Fridays (~32 hrs) | Budget | £0 |

1. Project Overview

This project produces five outputs across eight Friday sessions: a Power BI dashboard (5 analytical views), a written analysis (800–1,200 words), a LinkedIn article (500–600 words), a GitHub portfolio repository, and a master research log. The analytical scope covers five themes: AI adoption patterns, governance and strategy gaps, capacity and literacy, ethics and bias risk, and structural equity.

The project's analytical spine is this argument: the charity and nonprofit sector is adopting AI faster than it can govern, understand, or use it responsibly — and the costs of that gap fall disproportionately on the most vulnerable people those organisations exist to serve.

2. Milestones at a Glance

| Session | Date | Phase | Primary Milestone |
| --- | --- | --- | --- |
| 1 | Fri 11 Apr | Discovery | GitHub repo live. Research log started. Key sources downloaded. |
| 2 | Fri 18 Apr | Discovery | All sources read & logged. Data cleaned. Power BI connected. |
| 3 | Fri 25 Apr | Build | Views 1 & 2 built (Adoption + Governance Gap). |
| 4 | Fri 2 May | Build | Views 3, 4 & 5 built (Capacity, Ethics, Equity). |
| 5 | Fri 9 May | Polish | Dashboard complete & checked. Written analysis drafted. |
| 6 | Fri 16 May | Polish | Written analysis revised. LinkedIn article drafted. |
| 7 | Fri 23 May | Buffer / Flex | Buffer for overruns (house completion likely around this period). |
| 8 | Fri 29 May | Publish | All outputs live. CV & LinkedIn updated. Project retrospective written. |

3. Detailed Session Plans

Phase 1: Discovery & Setup (Sessions 1–2)

| Session 1 — Friday 11 April 2026 | ~4 hrs |
| --- | --- |

Objective: Set up the project infrastructure and begin data acquisition.

Tasks

- Create public GitHub repository: name it 'charity-nonprofit-ai-analysis'. Add README.md with project title and brief description. Create folders: /docs, /data, /analysis.

- Copy this BRD and project plan into /docs as PDF or markdown.

- Create master research log in Excel: columns — Stat | Source | Year | URL | Methodology notes | View | Confidence (H/M/L).

- Download Charity Commission full register (TSV format). Open in Excel using Power Query — filter columns to: charity name, income band, region, cause, expenditure, employee count.

- Download / bookmark Zoe Amar 2024 Digital Skills Report — begin reading. Log all statistics relevant to the five themes.

- Download / bookmark Phoenix/NCVO State of AI in Charities 2025 — skim structure, note key sections to read in Session 2.

- Bookmark: arxiv NGO systematic review (arxiv.org/abs/2510.15509) — read abstract and conclusions.

- Bookmark: Virtuous 2026 Nonprofit AI Adoption Report summary (nonprofitpro.com).

- End of session: research log should have 15+ entries.

Deliverable: GitHub repo live. Research log with 15+ entries. Charity Commission data open in Excel.

Watch out: The Charity Commission TSV is large. Use Power Query: Data > Get Data > From Text/CSV, then filter columns on load rather than after. If Excel crashes, open only the first 100k rows to explore structure first.

| Session 2 — Friday 18 April 2026 | ~4 hrs |
| --- | --- |

Objective: Complete reading, finish data cleaning, connect Power BI.

Tasks

- Read Zoe Amar 2025 report. Log all stats — particularly governance, literacy, and size segmentation data.

- Read NCVO Road Ahead 2025 — log context stats on funding pressures and digital divide.

- Read Bridgespan 2025 pieces (both) — log capacity and ethics stats.

- Read Chronicle of Philanthropy / Fast Forward piece — log small nonprofit AI data.

- Skim EU AI Act summary for charities — note which categories are 'high risk.'

- Build five clean Excel tabs — one per analytical theme. Move all logged stats into the correct tab, formatted for Power BI import.

- Open Power BI Desktop. Connect to your Excel workbook. Verify all five tabs load correctly.

- Sketch rough layout for each of the five dashboard views — pen and paper or sticky notes. Identify what chart type serves each question.

- Write a 200-word 'Data Gap Summary' noting the five most significant things the evidence cannot answer. Save to /analysis in GitHub.

Deliverable: All sources read and logged (target: 40+ entries). Five clean Excel tabs. Power BI connected. Data Gap Summary written.

Watch out: Don't try to make the data perfect before moving to build phase. Good enough for a portfolio project is: every stat has a source, every source is accessible, nothing is invented.

Phase 2: Dashboard Build (Sessions 3–4)

| Session 3 — Friday 25 April 2026 | ~4 hrs |
| --- | --- |

Objective: Build Views 1 and 2.

Tasks

- VIEW 1 — Adoption Patterns: Line chart — AI adoption % by year (2024, 2025, 2026). Grouped bar — adoption by org size (large/medium/small). Split bar or doughnut — strategic vs experimental use. Callout card: '88% use AI daily — but only 46% use it strategically.'

- VIEW 2 — Governance Gap: Four-metric comparison bar chart: adoption % vs policy % vs strategy % vs measurement % by year. Timeline of governance indicator growth (2024–2026). Callout card: '82% use AI. Under 10% have a policy governing its use.' Add 'Data Gaps' text card.

- Apply consistent colour theme across both views. Suggested palette: Navy (#1F3864) for headers, teal (#1F6B75) for positive findings, amber (#C55A11) for warnings, red for critical gaps.

- Add dashboard title (phrased as a question), subtitle, and source annotation to each view.

- Publish draft to Power BI Public — save and note the URL.

Deliverable: Views 1 and 2 built and published to Power BI Public.

Watch out: Power BI's card visual is excellent for callout stats. Use it liberally — 2–3 per view. The visual impact of a single bold number ('Only 9% feel ready to adopt AI responsibly') is stronger than any chart.

| Session 4 — Friday 2 May 2026 | ~5 hrs |
| --- | --- |

Objective: Build Views 3, 4 and 5. This is the longest session.

Tasks

- VIEW 3 — Capacity & Literacy: Budget allocation doughnut (1% training vs 54% hardware). Skill self-assessment bar chart (% rating themselves poor/fair/good). Training provision trend. Stacked bar: barriers by type. Callout: 'Only 1% of nonprofit tech budgets go to training.'

- VIEW 4 — Ethics & Bias Risk: This view is primarily qualitative. Build a matrix table in Power BI showing: AI use case (rows: triage, content, HR, fundraising, service delivery) vs harm risk (Low/Medium/High) vs governance provision (None/Partial/Formal). Use conditional formatting for colour. Add 3–4 callout cards for specific bias findings. Note clearly this is a qualitative synthesis, not quantitative data.

- VIEW 5 — Who Gets Left Behind: Charity Commission data — map or bar chart of charity income by UK region. Overlaid with readiness divide stats from Virtuous 2026. Callout: 'One fifth have governance in place. The majority use AI without structure to scale it.' Add note on global data gap (no equivalent regional breakdown available for Global South NGOs).

- Assemble all five views into a single Power BI report file. Check navigation between views.

- Test on mobile browser — note any layout fixes needed.

Deliverable: All five views built. Full dashboard assembled and published to Power BI Public.

Watch out: View 4 is the hardest to build well because the data is qualitative. Don't pretend it's quantitative. A clearly labelled 'analytical framework' table is more honest and more impressive than a fabricated chart.

Phase 3: Written Outputs (Sessions 5–6)

| Session 5 — Friday 9 May 2026 | ~4 hrs |
| --- | --- |

Objective: Refine dashboard. Draft written analysis.

Tasks

- Dashboard review: cross-check every statistic against the research log. Fix any inaccuracies. Add any missing source annotations.

- Mobile layout fixes from Session 4 testing.

- Begin written analysis. Target structure: Introduction (150 words, frame the problem); Theme 1–5 (100–150 words each — one key finding + one implication per theme); Conclusion & Recommendations (200 words — one recommendation each for charities, funders, policymakers); References (list all sources cited).

- Write to a charity sector professional — not a data specialist. Avoid jargon. Every paragraph should answer: 'so what does this mean for the people running charities?'

- Save draft to /analysis in GitHub.

Deliverable: Polished dashboard. Written analysis first draft (target: 800+ words).

Watch out: The written analysis is the output that will get shared most widely in the long run. Invest time in it. The conclusion's three recommendations are the most important part — make them specific, realistic, and evidenced.

| Session 6 — Friday 16 May 2026 | ~3 hrs |
| --- | --- |

Objective: Revise written analysis. Draft LinkedIn article.

Tasks

- Read written analysis aloud — this catches awkward phrasing faster than re-reading silently.

- Revise for clarity, flow, and tone. Ensure every paragraph earns its place.

- Finalise written analysis. Push to GitHub /analysis folder.

- Draft LinkedIn article (500–600 words). Structure: Hook stat (1–2 sentences); Problem framing (2–3 sentences); 3 key findings (one paragraph each); 1 call to action; Link to dashboard and GitHub.

- LinkedIn article tone: first person, conversational, confident. 'Here is what I found' not 'the data suggests.'

- Save LinkedIn article draft. Do not publish yet — publish in Session 8 after buffer.

Deliverable: Written analysis final. LinkedIn article draft ready to publish.

Watch out: LinkedIn native articles (not posts) are indexed by search and persist on your profile. Use the native article editor, not a link post. Add a cover image — even a simple screenshot of your dashboard view.

Phase 4: Buffer, Publish & Close (Sessions 7–8)

| Session 7 — Friday 23 May 2026 | ~2–4 hrs (flex) |
| --- | --- |

Objective: Buffer session. Use for overruns, house move admin, or advancing to Session 8 tasks.

Tasks

- If ahead of schedule: begin finalising GitHub README. Update any dashboard content from new research.

- If on schedule: rest. This period may coincide with house completion. Protect your energy.

- If behind: catch up on whichever written output is incomplete. The dashboard is the minimum viable output — prioritise it if forced to choose.

Deliverable: Flexible — depends on progress.

Watch out: This buffer exists because your house completion is likely around this period. Do not sacrifice it to get ahead on the project. The project serves your career, not the other way around.

| Session 8 — Friday 29 May 2026 | ~3 hrs |
| --- | --- |

Objective: Publish everything. Update professional profiles. Close the project.

Tasks

- Final review of dashboard — check all five views, all callout stats, all source annotations.

- Finalise GitHub README: project overview, links to all outputs, 'What I learned' section (3–5 honest sentences about what building this project taught you — this is what interviewers often ask about).

- Push all final files to GitHub: /docs (BRD + project plan), /data (Excel files + research log), /analysis (written analysis).

- Publish LinkedIn article. Add dashboard URL and GitHub link to LinkedIn Featured section.

- Add 'Portfolio' section to CV: project title, one sentence description, Power BI Public URL, GitHub link.

- Write a 3-sentence retrospective in the GitHub README: what you'd do differently, what surprised you, what you'd research next.

- Update your April/May Notion action log.

Deliverable: All five outputs live and linked. CV and LinkedIn updated. Project closed.

Watch out: This is the reward session. Don't skip it. The LinkedIn post, the GitHub README 'What I learned' section, and the CV update are where the career value actually lands.

4. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| House completion falls in project window — significant time/energy consumed | High | 1–2 sessions lost | Session 7 is a dedicated buffer. Dashboard is the minimum viable output if forced to cut. |
| Power BI work licence not permitted for personal use | Low | Tool switch needed | Check employer policy Week 1. If blocked, switch to Tableau Public — add one session for learning curve. |
| Key sources paywalled or unavailable | Low | Data gaps widen | All listed sources verified as free. Alternatives exist for each category. |
| Scope creep — adding more themes or outputs | Medium | Overrun | Lock scope to 5 themes and 5 outputs. Ideas for future phases go in the GitHub README 'Future work' section. |
| Analysis becomes too descriptive — not analytical | Medium | Weaker portfolio | Every chart must answer a question, not just show a number. The data gap finding is your strongest differentiator — feature it prominently. |

5. GitHub Setup — First Steps

GitHub is free and does not require technical coding knowledge. You are using it as a documentation and portfolio platform, not a code repository.

- Go to github.com and create a free account if you don't have one. Use your professional name.

- Create a new public repository. Name: charity-nonprofit-ai-analysis. Description: 'Portfolio project analysing AI adoption, governance gaps, and equity in the charity and nonprofit sector (2026).'

- Create a README.md file — GitHub will prompt you. Paste in the project title and a one-paragraph description for now. You will expand this in Session 8.

- Create four folders by adding placeholder files: /docs/placeholder.md, /data/placeholder.md, /analysis/placeholder.md.

- Share the repository URL on your LinkedIn profile 'About' section immediately — even when empty, it signals that you document your work.

Your GitHub profile is increasingly viewed by hiring managers before interviews in data-adjacent roles. Having a public, well-documented project repository — even a work-in-progress one — is a significant differentiator for BA roles that require data capability.

6. LinkedIn Article — Writing Guide

A LinkedIn native article (published via 'Write article' not 'Start a post') is indexed by LinkedIn search and Google, lives permanently on your profile, and signals a different level of professional investment than a post.

| Section | Target length | Guidance |
| --- | --- | --- |
| Hook | 1–2 sentences | Lead with the most striking stat. E.g.: 'Charities are using AI every day. Only 1 in 10 has a policy governing it. That gap is a governance crisis — and it's falling hardest on the people charities exist to help.' |
| Why this matters | 2–3 sentences | Explain the real-world stakes. Not abstract — specific. Who gets harmed when AI goes ungoverned in a food bank or an employability charity? |
| 3 Key findings | One paragraph each (~80 words) | One from adoption/governance, one from capacity/literacy, one from ethics/equity. Each should end with a 'so what?' implication. |
| What needs to change | 3–4 sentences | One recommendation each for: charities themselves; funders; and sector bodies/policymakers. Be specific. |
| Call to action + links | 2–3 sentences | 'I've built a dashboard exploring this in more detail — link here. The full analysis is on GitHub — link here. If you work in this space, I'd welcome your perspective.' |

7. Success Criteria

| Criterion | Measure |
| --- | --- |
| Dashboard live | Power BI Public URL accessible on any device, no login required |
| All five views present and accurate | Every stat cross-checked against research log |
| GitHub repository public and complete | README, /docs, /data, /analysis all populated |
| Written analysis published | 800–1,200 words in /analysis folder |
| LinkedIn article published | Native article live, links to dashboard and GitHub |
| CV updated | Portfolio section with dashboard URL and GitHub link |
| Research log complete | Every stat in dashboard traceable to a named source |
| Project complete by 29 May 2026 | Within 8 Friday sessions, £0 cost |